## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US1 | Overview - The Aadhaar Fraud Management System automates the detection of fraudulent Aadhaar documents using machine learning models. It processes images to classify, detect, and extract text from Aadhaar cards, ensuring accuracy in verification. | MUST HAVE | NO | Mentor - 521 | 3- Completed
S2 | S2 | US2 | Workflow - Users upload files, which are processed through classification, detection, and OCR models. The system extracts data, compares it with metadata, and displays match scores. | MUST HAVE | NO | Mentor - 521 | 3- Completed
S3 | S3 | US3 | Document Usecase - The system validates Aadhaar documents to prevent fraud in identity verification processes like bank accounts and government services. | SHOULD HAVE | NO | Mentor - 521 | 3- Completed
S4 | S4 | US4 | Knowledge of Model - The system uses Aadhaar document processing: YOLO for classification and detection tasks, and EasyOCR for optical character recognition. These models are trained to recognize Aadhaar cards and extract relevant data with high accuracy. | MUST HAVE | Research Papers | Mentor - 521 | 3- Completed
S5 | S5 | US5 | Classification Model - The classification model, based on YOLO, distinguishes Aadhaar cards from other documents. It analyzes images and classifies whether a document is an Aadhaar card or not, ensuring only valid documents are processed further. | MUST HAVE | YOLO | Mentor - 521 | 3- Completed
S6 | S6 | US6 | Detection Model - The detection model, also based on YOLO, identifies key fields within an Aadhaar card, such as the name, UID, and address. It locates these fields in the image for precise cropping and text extraction. | MUST HAVE | YOLO | Mentor - 521 | 3- Completed
S7 | S7 | US7 | OCR Model - EasyOCR is used to extract textual data from the cropped sections of the Aadhaar card. This model reads text from different regions (like name, UID, address) with high accuracy to assist in the comparison process. | MUST HAVE | EasyOCR | Mentor - 521 | 3- Completed
S8 | S8 | US8 | Backened - The backend, built using Flask, handles file uploads, model predictions, and data extraction. It processes user requests, loads the necessary models, runs predictions, and returns the results as JSON to the frontend. | MUST HAVE | Flask | Mentor - 521 | 2- In Progress
S9 | S9 | US9 | Frontend - The frontend, implemented with HTML, CSS, and JavaScript, provides a user-friendly interface for uploading files, displaying match results, and interacting with the backend. | MUST HAVE | HTML, CSS, Javascript | Mentor - 521 | 2- In Progress
S10 | S10 | US10 | Connecting Backend and Frontend - The Flask backend and frontend are connected via HTTP requests. When the user uploads files, the frontend sends a POST request to the backend, which processes the files and returns the results. | MUST HAVE | AJAX | Mentor - 521 | 2- In Progress
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 42 | 5 | 6 | 6 | 6 | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Introduction to Project and Overview of it | 2024-12-05 | 2024-12-07 | Shine Suri | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TID-02 | Workflow Creation and Project Goal Document | 2024-12-07 | 2024-12-11 | Shine Suri | Design | 3- Completed | 4 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TID-03 | Use Case Research and Preparation | 2024-12-11 | 2024-12-12 | Shine Suri | Others | 3- Completed | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TID-04 | Preprocessing of dataset and to implement YOLO for classification and detection tasks | 2024-12-12 | 2024-12-16 | Shine Suri | Coding | 3- Completed | 6 | 0 | 1 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TID-05 | YOLO-based classification model to distinguish Aadhaar cards from other documents | 2024-12-16 | 2024-12-23 | Shine Suri | Coding | 3- Completed | 6 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | TID-06 | YOLO-based detection model to identify key fields within an Aadhaar card | 2024-12-23 | 2025-01-02 | Shine Suri | Coding | 3- Completed | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | TID-07 | EasyOCR-based model to extract textual data from cropped sections | 2025-01-02 | 2025-01-09 | Shine Suri | Coding | 3- Completed | 4 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-008 | TID-08 | Project Discussion Module 1(Flask-based backend to handle files) | 2025-01-09 | 2025-01-16 | Shine Suri | Build | 2- In Progress | 6 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | TID-09 | Project Discussion Module 2(frontend for file uploads and interacting with the backend) | 2025-01-16 | 2025-01-16 | Shine Suri | Coding | 2- In Progress | 5 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | TID-10 | Project Discussion Module 3(Integrating backend with frontend processing requests through HTTP POST to return results) | 2025-01-22 | 2025-01-24 | Shine Suri | Integration Test | 2- In Progress | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Delayed file processing due to insufficient data validation | Improved validation checks to handle incorrect data formats
Sprint 2 | Day 4 | Integration issues with models and frontend | Coordinated with the mentor
Sprint 3 | Day 6 | Inconsistent results from detection model | Fine-tuned model parameters
Sprint 4 | Day 7 | Slow system performance during heavy load | Optimized backend and model performance
Sprint 5 | Day 9 | Agile template confusion | Conducted detailed discussion with mentor
Sprint 6 | Day 12 | Difficulty in identifying all potentional use cases due to incomplete information | Conducted online research and consulted online resources to fill gap
Sprint 7 | Day 16 | Confusion about prioritizing use cases for preparation | Created priority matrix to evaluate
Sprint 8 | Day 23 | Challeneges in integration of backend | Conducted detailed discussion with mentor

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2024-11-05 | 2024-12-08 | Shine Suri | learning about the models | work on unrelated projects | Flask backend for handling requests | Set up environment and models
2 | Sprint 2 | 2024-11-16 | 2024-12-18 | Shine Suri | Began implementing classification model and integrating YOLO | backend development work | integrating EasyOCR for text extraction | detection and text extraction
3 | Sprint 3 | 2024-11-23 | 2024-12-27 | Shine Suri | frontend for uploading files | incomplete frontend designs | refining backend logic for image processing and model prediction | frontend design and ensured file upload works with backend
4 | Sprint 4 | 2025-01-02 | 2025-01-06 | Shine Suri | frontend with Flask backend, ensuring HTTP requests work | testing without integration | testing and debugging the models | integration of frontend with backend
5 | Sprint 5 | 2025-01-12 | 2025-01-15 | Shine Suri | Adding functions for comparing extracted data and displaying match scores | manual result verification process | model accuracy and error handling | system's ability to compare extracted data
6 | Sprint 6 | 2025-01-17 | 2025-01-20 | Shine Suri | Started on deployment | working on non-critical features | model performance and backend stability | deployment but still refining final setup
7 | Sprint 7 | 2025-01-23 | 2025-01-07 | Shine Suri | Project documentation integration | testing in non-production environments | testing the system and refining | final checks